## Client Services Training Plan
S.No | CVS KT Topics | Day | Week | P.Start Date | P.End Date | A.Start Date | A.End Date | Status | Comments
Basic Training
1 | Healthcare Basics and Functional Testing | Day 1 | Week 1
2 | Basics of Pharmacy Benefits | Day 1 | Week 1
3 | Excel Fundamentals | Day 1 | Week 1
4 | Introduction to Testing Tools | Day 2 | Week 1
5 | SFDC Walkthru & Usage | Day 2 | Week 1
6 | Client Requirement Walkthru Part 1 | Day 3 | Week 1
7 | Client Requirement Walkthru Part 2 | Day 3 | Week 1
8 | Introduction to Claims Testing | Day 4 | Week 1
9 | EZ Test, Members, Claim, GPI, NDC Pull | Day 4 | Week 1
10 | Basics of Benefits Scenarios & Testing | Day 5 | Week 1
11 | Basics of Clinical Scenarios & Testing | Day 5 | Week 1
12 | Introduction to Query Testing | Day 6 | Week 2
13 | Query Testing - Benefits | Day 6 | Week 2
14 | Query Testing - Clinical | Day 6 | Week 2
15 | Traditional & Xref plan, CLC | Day 7 | Week 2
16 | RXClaim Navigation | Day 7 | Week 2
Plan Benefits
1 | NIF Query | Day 8 | Week 2
2 | NIF Claims | Day 8 | Week 2
3 | Tier Status, Days Supply | Day 9 | Week 2
4 | TF window/Cumulative, Emergency Supply, New Patient, Renew Member | Day 9 | Week 2
5 | Copay | Day 10 | Week 2
6 | Accums (Ded and OOP) | Day 10 | Week 2
7 | Deductible Limits & Reset and MOOP | Day 11 | Week 3
8 | Deductible Exclusion Tier & GPIs | Day 11 | Week 3
9 | Maximum Out of Pocket Limits & Reset | Day 11 | Week 3
10 | Maximum Allowable Benefits | Day 11 | Week 3
11 | Lifetime/Annual MAB | Day 11 | Week 3
12 | Diagnosis Required | Day 12 | Week 3
13 | Excluded Drugs | Day 12 | Week 3
14 | Refill Threshold | Day 12 | Week 3
15 | Part B Drug Coverage/Drug Coverage | Day 13 | Week 3
16 | OCC (Secondary Coverage and COB) | Day 14 | Week 3
17 | Balance on Hand | Day 14 | Week 3
18 | Automated Overrides | Day 14 | Week 3
19 | SCC Code (03,04, 05 and 13) | Day 14 | Week 3
20 | Prescribers, NPI - Including Excluded Prescribers | Day 15 | Week 3
21 | Excluded Prescribers (State and Federal) and Pharmacy | Day 15 | Week 3
22 | FML | Day 16 | Week 4
23 | CMS Labeller | Day 17 | Week 4
24 | Natural Disaster and emergency situations | Day 17 | Week 4
25 | EGWP or STCOB | Day 18 | Week 4
26 | Vaccine | Day 18 | Week 4
27 | Seasonal, Non Seasonal & Travel Vaccines | Day 18 | Week 4
28 | COVID Testing - Vaccine, OTC Test Kit and Antiviral | Day 19 | Week 4
29 | Script Sync | Day 19 | Week 4
30 | DUR | Day 20 | Week 4
31 | MIC - MIC, MIC Copay and MIC SCC 08 | Day 21 | Week 5
32 | DAW | Day 21 | Week 5
33 | ESRD | Day 22 | Week 5
34 | Government Claims | Day 22 | Week 5
35 | Transplant | Day 22 | Week 5
36 | Hospice Scenarios | Day 22 | Week 5
37 | High Cost Tier DS | Day 23 | Week 5
38 | LICS (1,2,3) Copayments | Day 23 | Week 5
39 | VBID | Day 23 | Week 5
40 | MOOP scenarios using Part B drugs | Day 23 | Week 5
41 | MedD Excluded scenarios | Day 24 | Week 5
42 | Opioid Coverage | Day 25 | Week 5
43 | OTC | Day 25 | Week 5
44 | Mchoice/Maintenance drug day supply | Day 26 | Week 6
45 | Prudent network coverage | Day 27 | Week 6
46 | HCR coverage | Day 28 | Week 6
47 | Emergency Supply for 3/5 days | Day 29 | Week 6
48 | Brand over generic | Day 29 | Week 6
49 | Third party exceptions | Day 29 | Week 6
50 | Network specific copay | Day 30 | Week 6
51 | High dollar rejection | Day 30 | Week 6
52 | Specialty day supply | Day 30 | Week 6
53 | Broader Vaccine with $0 and Custom Copayment | Day 31 | Week 7
54 | MedVac | Day 31 | Week 7
Formulary & Utilization Management
1 | Formulary Testing | Day 32 | Week 7
2 | Negative Formulary | Day 32 | Week 7
3 | SAM UM Validation | Day 33 | Week 7
4 | Prior Authorization (PA, HRM PA, BvD PA, New Start PA) and CPM | Day 34 | Week 7
5 | Quantity Limits, DD,QVT, Max Qty Fill | Day 35 | Week 7
6 | Multisource Code, Rx/OTC | Day 35 | Week 7
7 | Step Therapy | Day 36 | Week 8
8 | Duplicate Therapy | Day 36 | Week 8
9 | UPPL, Package vs Time, Package Max | Day 37 | Week 8
10 | Benefit Reset Date Specific testing (Rolled out only in MVP) | Day 37 | Week 8
11 | Min Age & Max Age, Age_Range | Day 38 | Week 8
12 | Gender, High Dollar, Amount Due | Day 38 | Week 8
13 | FVT, Maximum Days Supply, DSVT | Day 39 | Week 8
14 | Smart PA | Day 40 | Week 8

## High Level Plan
SL | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Technology | Functional Testing(6 hrs daily), ICT |  | Healthcare/CVS PBM/Benefits & Clinical Testing in both Claims and Query perspective (Daily 6 hrs) |  |  |  | Healthcare/CVS PBM/Benefits & Clinical Testing in both Claims and Query perspective (Complete Day of 9hrs)
| Java(3 hrs daily) |  | Selenium Automation(3 hrs daily)
Gating Criteria Evaluation |  |  | Interim Evaluation(By SMEs) |  |  | Final Evaluation
Common in all Weeks | BU SM connect for Functional Testing best practices, Deliverables review by SME, BU Healthcare leader connect, Daily Quiz and mock interviews
|  | ? |  | 3rd week virtual, 4thweek- ODC traiing
|  | Bootcamp+ 6 weeks |  | Week 3, 3rd day handson strarts for BU topic
|  |  |  | 5 | 5 | 3
|  |  |  | 25 | 25 | 15 | 80
|  |  |  | 20 | 20 | 12 | 64
[6 empty] | 18 | 36
| BU owned training | Validating with coaches/locatoin team |  | 1st cohort in chennai siruseri(30 members)
| PATs |  |  | Z id, citrix
| Business is okay to update DD |  |  | Lab client access
| Preferred location is coimbatore |  |  | 1% allocation …onboarding formalities
| no issues to supply |  |  | CVS access - only in odc
|  |  | Common training? | two days contents availabel in CTS sharepath and can be repurposed
|  |  | ODC, PMO ? | Training happens in common place monitoring by L&D coaches
|  |  | virtual training? | Did not go well.
15
12
18
45
client access
selenium lcaol
javal
BU topic

## Module List
Stage/Level | Course Segment | Course/Module | Delivery Method | Baseline Duration ( Hours ) | Day - Wise | Enablement Assured Level
Stage 1 | Agile Functional Testing and Integrated project | Functional testing which covers all types of testing Learn Agile and Jira STLC: Test Plannig, Test Development, Test Execution, Result Analysis, Bug Tracking and Reporting, Test Closure Activity Types of Testing (Unit testing, integration testing, Regression testing, etc.,) Automated functional tests for both front-end and back-end code Agile Testing + Jira Tool cognizant templates for Agile deliverables | Self-Paced Learning and ILT | 49 | Day 1 - 10 | Skill
|  | Integrated Capability Test (ICT) - Functional Testing | Assessment | 4 |  | Skill
|  | Business mentor connect | ILT | 2 |  | Skill
| Java Programming | Java Basic Programming, Applying Object Oriented Concepts, Collections Framework,Arrays & Strings ,Exception Handling Thread Handling,File Handling,JDBC Overview,Java 8 Basics Advanced Topics | Self-Paced Learning/ILT | 25 |  | Skill
|  |  | Tekstac / BU Driven Hands-on |  |  | Skill
| Stage 1 - Business Mentor Connect |  |  | 2 |  | Awareness
| Stage 1 - BH Training(Weekly 4 hours) |  |  | 8 |  | Skill
Stage 1 Functional Testing ICT |  |  |  | 4 | Day 10 | Assessment
Stage 2 | Health Care Domain | Healthcare/CVS PBM/Benefits & Clinical Testing in both Claims and Query perspective CVS access | Self-Paced Learning/ILT | 273 | Day 13 - 48 | Skill
|  | Hands-on | Tekstac / BU Driven Hands-on |  |  | Skill
|  | Project | Project |  |  | Skill
| Selenium Automation Concepts and Integrated project, GIT HUB copilot and GenAI | Automation Concepts, Selenium configuration, WebDriver Basics, Selenium Automation Techniques, Dynamic Xpath, POM and ApachePOI, TestNG,Fundamentals of Gen AI(Refer TOC_GEN AI Learnings), GitHub Copilot (Refer TOC_GitHub Copilot Coverage) | Self-Paced Learning/ILT | 53.5 |  | Skill
|  | Hands-on on Automation Testing | Assessment |  |  | Skill
|  | Automation Framework | Self-Paced Learning/ILT |  |  | Skill
| MOCK Evaluation through AI BOT |  | Evaluation | 1.5 |  | Evaluation
| Stage 2 - Interim Technical Evaluation |  |  | 27 | Day 23 - 25
| Stage 2 - Final Technical Evaluation |  |  | 18 | Day 48 - 50 | Evaluation
|  |  | Total Duration(in hours) | 467
|  |  | Total Duration(in Days) | 52
|  |  | Weeks | 10.4

## About Curriculum
Healthcare Functional and Automation
1. Name of the track | Healthcare Functional and Automation
2. Category (Technical/Domain/Behavioral): | Technical and Behavioral
3. Outcome Expected | Delivery Readiness trainees
4. Measureable units of the outcome | Trainees should be able to contribute developing test strategies and design robust automation frameworks. Should be able to efficiently automate test cases using Selenium API ensuring accurate and reliable execution and management of test cases. Collaborate with automation leads on test case design for comprehensive coverage and involve in Script Development, review, and maintain automation scripts. Make environment Setup to ensure correct test environments are ready and do CI/CD Integration: Integrate automation into CI/CD pipelines for continuous testing. Ensure to manage and maintain test data sets and Oversee test execution, monitor results, and generate reports. Identify and address performance bottlenecks and Troubleshoot and resolve automation issues.
5. Who are the target audience? | PT\PAT
6. What is the Gating Criteria? | A GREEN as PHS in the Final Evaluation
7. Duration | 10 Weeks

## Performance Outcome
Sno | Learning Outcome | Performance Outcome | Level (Awareness, Skill and Knowledge) | Sub Track
1 | Associate shoud have ability to solve business problems using Java Programming Language | He / She should be able to explain features of Java, and model of the Java programming language(knowledge) | Skill | Core Java
|  | He / She should be able to describe and et environment variables to allow the Java compiler and runtime executables to function properly | Skill
|  | He / She should be able to implement Core java language fundamentals, control flow statements, Operators and create java objects | Skill
|  | He / She should be able to implement constructor, Access Specifiers concepts, encapsulation, Inheritance, Abstraction, Overloading, Overriding & Polymorphism using core java programming | Skill
|  | He / She should be able to Illustrate Java code that uses variables, arrays, conditional and loop constructs to achieve program objectives | Skill
|  | He / She should be able to implement Exception handling using java | Skill
|  | He / She should be able to implementString API to manipulate numeric, text, and string data using appropriate Java operators | Skill
|  | He / She should be able to applyand create dynamic programming in java using Collection & Util API's | Skill
|  | He / She should be able to implement streams using IO Stream API's & File API’s in java | Skill
|  | He / She should be able to implement JDBC to provide a program level interface for communicating with database using java programming | Skill
3 | Associate should have ability to work in different phases of the Functional Testing Life Cycle for a given business requirement by adhering to organizational standards and processes. | He / She should be able to define agile implementations and software testing, unit test, integration test, regression test, and system testing. | Skill | Functional Testing
|  | He/ She should be able to Illustrate the different phases of the Functional Testing’s life cycle for the given business requirement. | Skill
|  | He/ She should be able to analyze requirement and prioritize | Skill
|  | He/ She should be able to recognize testable and non testable requirements | Skill
|  | He/ She should be able to define test strategy , test plan and its importance | Skill
|  | He/ She should be able to design test scenarios(both positive and negative) from requirements gathered. | Skill
|  | He/ She should be able to design test cases from test scenarios | Skill
|  | He/ She should be able to perform the test execution based on the test cases prepared. | Skill
|  | He / She should be able to define a defect. | Skill
|  | He/ She should be able to list the defect status in defect life cycle | Skill
|  | He/ She should be able to identify cases mismatching with the requirements and log defect. | Skill
|  | He / She should be able to define regression testing | Skill
|  | He/ She should be able to perform regression testing | Skill
|  | He/ she should able to describe test closure and it importances. | Skill
4 | Associate should have the ability to write and execute test scripts using selenium, to automate the functionalities of a web application | He / She should be able to describe the Selenium automation tool in detail with its components and principles | Skill | Selenium Automation with Project Deliverables
|  | He / She should be able to implement proof of concepts(Feasibility study), create automated structured scripts for Smoke suite and Regression suite | Skill
|  | He / She should be able to illustrate Selenium API’s to run robust test scripts on web applications on multiple browsers | Skill
|  | He / She should be able to implement locator Techniques & Tools used to identify elements/objects | Skill
|  | He / She should be able to illustrate TestNG Framework and Apache POI, Test Automation Frameworks with Page Object Model (POM) | Skill
|  | He / She should be able to illustrate creating and parsing JSON and XML file to externalize the test data from external source for selenium automation | Skill
5 | Associate should have ability to use Git and GitHub commands, and Maven to manage the dependencies and plugins required for the project, CICD pipeline using Maven with Jenkins for selenium project. | He / She should be able to define continuous integration and its importance using Jenkin | Skill | Devops
|  | He / She should be able to explain installation and configuration settings to setup continuous Integration using Jenkin | Skill
|  | He / She should be able to explain job creation | Skill
|  | He / She should be able to explain Jenkin plugin | Skill
|  | He / She should be able to define continuous deployment and its importance using Maven tool | Skill
|  | He / She should be able to explain installation and configuration settings to setup continuous deployment using Maven tool | Skill
|  | He / She should able to describe Maven Build life Cycle | Skill
|  | He / She should able to describe the differences between Git, Github and Gitlab | Skill
|  | He / She should be able to implement Installation and configure Git ,manage files using CLI commands, and manage repositories | Skill
|  | He / She should be able to implement Selenium Grid to execute the tests on various environments/ platforms/ machines | Skill
6 | Associate should have ablity to demonstrate the functionalities of Healthcare and Facets domain and do the testing on the respective products | He / She should be able to describethe Healthcare fundamentals and evolution Of Health Plans & Affordable Care act | Knowledge | Healthcare and Facets
|  | He / She should be able to implement Basic Concepts of Health Insurance, Health Plan Benefits and Networks, Provider Compensation Methods, Various Types Health Plans, Consumer Directed Health Plans, Provider Organizations, Utilization Management and Review Underwriting, Rating and Financing Claim Administration, Government Programs | Skill
|  | He / She should be able to illustrate FACETS fundmentals Group, Subgroup and Class/Plan Configuration, Enrollment Member & Eligibility, Configure Provider Agreements & Provider Network Relationships, Claims Entry, Medical & Hospital Claim processing, Customer Service | Skill

## TOC_BU Core Java
Core Java - TOC
Section | Chapter | Chapter Name | Topic | Training Mode
Java Basics | Chapter-1 | Introduction to Java,Data Types and Variables | History & Features of Java: OOP, platform independence, JVM, JDK, JRE | In-Person Trainer - ILT (ILT - Instructor Led Training)
Data Types: Primitive and non-primitive types, Variable declaration, Type casting
Overview of 3 tier application with middleware
|  |  | HandsON : Day 1 Topics - TekStac Lab | Daily Lab Exercise(DLE)
Object- Oriented Programming (OOP) Concepts | Chapter-2 | OOP Basics | Object-Oriented Principles: Encapsulation, Inheritance, Polymorphism, Abstraction | In-Person Trainer - ILT
Classes and Objects: Class structure, Object creation, Instance variables
Constructors: Default constructor, Parameterized constructor, Constructor overloading
| Chapter-3 | Inheritance,Abstraction & Encapsulation | Inheritance: Single inheritance, Multilevel inheritance, super keyword
|  |  | HandsON : Day 2 Topics - TekStac Lab | Daily Lab Exercise(DLE)
|  |  | Polymorphism: Method overloading, Method overriding | In-Person Trainer - ILT
Abstraction: Abstract classes, Interfaces
|  |  | HandsON : Day 3 Topics - TekStac Lab | Daily Lab Exercise(DLE)
|  |  | Encapsulation: Access modifiers (public, private, protected), Encapsulating data | In-Person Trainer - ILT
| Chapter-4 | Keywords | Static Members: Static variables, Static methods, Static blocks
|  |  | HandsON : Day 4 Topics - TekStac Lab | Daily Lab Exercise(DLE)
|  |  | this and super: Referring current object, Accessing parent class methods | In-Person Trainer - ILT
final Keyword: Final variables, Final methods, Final classes
Arrays & Strings | Chapter-5 | Arrays,Strings,StringBuffer & StringBuilder | Arrays: One-dimensional array, Multidimensional array, Array traversal and operations
Strings:String class, Immutability, String methods: length, substring, equals, etc.
|  |  | HandsON : Day 5 Topics - TekStac Lab | DLE & BU Connects
|  |  | StringBuffer & StringBuilder: Mutability, Common methods: append, insert, delete | In-Person Trainer - ILT
Exception Handling | Chapter-6 | Exception Handling | Types of Exceptions: Checked exceptions, Unchecked exceptions
|  |  | HandsON : Day 6 Topics - TekStac Lab | DLE & BU Connects
|  |  | try-catch Block: Single try-catch, Multiple catch, finally block | In-Person Trainer - ILT
throw and throws: Manually throwing exceptions, Propagating exceptions
|  |  | HandsON : Day 7 Topics - TekStac Lab | DLE & BU Connects
|  |  | Custom Exceptions: Creating custom exceptions | In-Person Trainer - ILT
Collections | Chapter-7 | Java Collections | Introduction to Collections: Collection hierarchy, Collection interfaces (List, Set, Map)
|  |  | HandsON : Day 8 Topics - TekStac Lab | DLE & BU Connects
|  |  | List Interface: ArrayList, LinkedList, Vector, Stack | In-Person Trainer - ILT
Set Interface: HashSet, LinkedHashSet, TreeSet
|  |  | HandsON : Day 9 Topics - TekStac Lab | DLE & BU Connects
|  |  | Map Interface: HashMap, LinkedHashMap, TreeMap, Hashtable | In-Person Trainer - ILT
Iterator: Iterator, ListIterator
|  |  | HandsON : Day 10 Topics - TekStac Lab | DLE & BU Connects
|  |  | Comparable & Comparator: Sorting with Comparable, Sorting with Comparator | In-Person Trainer - ILT
Thread Handling | Chapter-8 | Java Thread Handling | Introduction to Threads: Thread vs Process, Thread lifecycle
Creating Threads: Extending Thread class, Implementing Runnable interface
Thread Methods: sleep(), join(), start(), run()
|  |  | HandsON : Day 11 Topics - TekStac Lab | DLE & BU Connects
File Handling | Chapter-9 | Java File Handling | Character Streams: FileReader, FileWriter, BufferedReader, BufferedWriter | In-Person Trainer - ILT
File Handling: File class, File reading and writing (FileInputStream, FileOutputStream)
|  |  | HandsON : Day 12 Topics - TekStac Lab | DLE & BU Connects
JDBC Overview | Chapter-10 | JDBC (Java Database Connectivity) | JDBC API Overview: JDBC architecture, Driver Manager, Statement and PreparedStatement | In-Person Trainer - ILT
CRUD Operations: Insert, Update, Delete, Select Queries
Transactions: Commit, Rollback, Savepoints
|  |  | HandsON : Day 13 Topics - TekStac Lab | DLE & BU Connects
Java 8 Basics | Chapter-11 | Java 8 Features | Lambda Expressions: Lambda syntax, Functional interfaces | In-Person Trainer - ILT
Stream API: Stream operations (filter, map, reduce)
Optional Class: Avoiding NullPointerException with Optional
Advanced Topics | Chapter-12 | Generics & Annotations | Generics: Generic classes, methods & wildcards
|  |  | HandsON : Day 14 Topics - TekStac Lab | DLE & BU Connects
|  |  | Annotations: Built-in annotations (@Override, @Deprecated) & Custom annotations | In-Person Trainer - ILT
| Chapter-13 | Design Patterns | Design Patterns: Singleton, Factory, Observer, Strategy patterns
|  |  | HandsON : Day 15 Topics - TekStac Lab | DLE & BU Connects
Total Hours
#REF!
|  | Real Time Project | Mini Assignments on Core Java
Hackathon on Core Java
Interview Preparations on Core Java

## QEA Basics - Stage 1 (hidden)
Stage 1 - QEA Basics Learning Path
MileStones | Skill | Topics | Weeks | Mode | Course Name | Course Topics | Course URL | Duration in hours | Outcomes | Objectives
Functional Testing | Agile | Agile Fundamentals | 1 Week | Learning | The Complete 2022 Software Testing Bootcamp | Section 2: Basics Concepts of Software Testing Section 3: Test Case Writing Section 4:Test Execution & Bug reporting Section 5: Real Testing Project: How to write test scenarios from Requirement Section 6: Black Box Test Techniques Section 7: How to Use Test Link Section 8: Basics of Agile & Agile Testing Section 10: Freelance Testing websites Section 11: White Box Test Techniques | https://cognizant.udemy.com/course/testerbootcamp/ | 8.5 | This course is designed to introduce basics of Agile methodologies & Agile Testing Basics of Software Testing Test case & Bug Report Writing Implementing the test process on a Test Management Tool (Testlink) Basics of Agile methodologies & Agile Testing How to use Application Lifecycle Management Tool (JIRA) How to become a Freelance Tester Basics on Automation Testing Basics of Performance Testing using Jmeter Basics of API Testing Basics of Mobile Testing using Simulators & Emulators How to write a professional QA Resume How to prepare for a QA Interview Different certificates in Software Testing Field and how to apply on them | This course is designed to introduce basics of Agile methodologies & Agile Testing. This course is designed to introduce learner to software testing life-cycle, different levels of testing, test environment setup, test case design technique, test data creation, test execution, bug reporting, and other essential concepts of software testing. Also covers Basics on Automation Testing, Performance Testing , API Testing, Mobile Testing
| Functional Testing | Testing fundamental - STLC
Integrated Capability Test (ICT) - Functional Testing (SBA)
Java Programming | Java | Java programming | 2 weeks | Learning | Java: Java In-Depth: Become a Complete Java Engineer! Core Java Made Easy (Covers the latest Java 17) JDBC: Java Database Connection: JDBC and MySQL | Java: Refer all the sections given in the handbook JDBC: Refer section 1 to 8 under the course Java Database Connection: JDBC and MySQL | Java: * https://cognizant.udemy.com/course/java-in-depth-become-a-complete-java-engineer/learn/lecture/2152258#overview *https://cognizant.udemy.com/course/corejavamadeeasy/learn/lecture/5634790#overview JDBC: https://cognizant.udemy.com/course/how-to-connect-java-jdbc-to-mysql/ | 25 | Learn the fundamentals of java and oops Learn the building blocks of a java program Handle Exceptions Read and Write files Use flow control and looping statements Implement encapsulation polymorphism inheritance and abstraction Write multi threaded programs Understand and use Garbage Collection Learn and create the different types of inner classes Understand and master Strings Learn collections in depth Use functional interfaces and lambda expressions Understand the internal of JVM Interview Question updated regularly All in quick and easy steps | This course enables the testers who want to learn java quickly and in depth for Selenium automation
GenC - QAQE-TECHNICAL-JAVA TRACK - CORE JAVA SKILL WAR - SKILL BASED ASSESSMENT [101-BASICS] -LAB_ATKJE072 (SBA)
Web UI, DataSource | Web UI | HTML+CSS+XPATH+XHTML+DOM | 2 Weeks | Learning | Build Websites from Scratch with HTML & CSS | Refer sections marked in the handbook | https://cognizant.udemy.com/course/build-website-scratch/learn/lecture/442294#overview | By the end of this course, you will have a basic & thorough understanding of HTML & CSS Upon completion, you will have coded a handful of useful HTML & CSS examples You focus on building a beautiful, semantic, HTML & CSS web page | By the end of this course, you will have a basic & thorough understanding of HTML & CSS Upon completion, you will have coded a handful of useful HTML & CSS examples You focus on building a beautiful, semantic, HTML & CSS web page | You will Learn HTML You will learn CSS You will get a certification after the course that you can print You will get the skills you need to make website
[5 empty] | Master XPath and CSS Selectors for Selenium WebDriver | Refer section 1, 2, 3, 4 and 5 in this Udemy course and complete the corresponding learnings. | https://cognizant.udemy.com/course/xpath-and-css-selectors/learn/lecture/15399452#overview | By the end of this course, you will have a basic & thorough understanding of WebElement Locating Strategies For Selenium WebDriver | By the end of this course, you will have a basic & thorough understanding of WebElement Locating Strategies For Selenium WebDriver | Locating Elements Using ID, Name, Class Creating XPath Creating CSS Selectors Using Locaters in Selenium WebDriver Scripts Using XPath and CSS in Selenium WebDriver Scripts
| Java script | Java script |  |  | Accelerated JavaScript Training | Refer section 1 to 9 in this Udemy course and complete the corresponding learnings. | https://cognizant.udemy.com/course/javascript-bootcamp-2016/learn/ | All the basics about variables, functions, operators, language features, built-in objects and much more! In-depth modules on Arrays, Objects & Prototypes, Functions, DOM Interaction, Events, AJAX and all the other core features that make JavaScript so important. | All the basics about variables, functions, operators, language features, built-in objects and much more! In-depth modules on Arrays, Objects & Prototypes, Functions, DOM Interaction, Events, AJAX and all the other core features that make JavaScript so important. | What you’ll learn: Use JavaScript to write modern, reactive Websites Understand how JavaScript works and how to use its many advantages Dive into JavaScript Libraries like jQuery
| Datasource | SQL + XML + JSON |  |  | SQL: SQL for Beginners: Learn SQL using MySQL and Database Design JSON & XML: Learn API Technical Writing: JSON and XML for Writers | SQL: Refer section 1 to 14 under the course SQL for Beginners: Learn SQL using MySQL and Database Design. JSON & XML: Refer section 1 to 4 under the course Learn API Technical Writing: JSON and XML for Writers. | https://cognizant.udemy.com/course/sql-for-beginners-course/learn/lecture/8435392#overview https://cognizant.udemy.com/course/api-documentation-1-json-and-xml/ | Understand SQL using the MySQL database. Learn Database Design and Data Analysis with Normalization and Relationships | Understand SQL using the MySQL database. Learn Database Design and Data Analysis with Normalization and Relationships | What you’ll learn: Have a detailed knowledge and understanding of using MySQL, one of the most widely used databases in the world. Obtained a knowledge of SQL, and MySQL, allows students to apply for jobs in the IT sector. In-depth knowledge of database design will give students an edge over other applicants.

## Selenium - Stage 2 (hidden)
Stage 2 - Selenium With Digital Technologies Learning path
MileStones | Skill | Weeks | Topics | Mode | Course Name | Course Topics | Course URL | Outcomes | Objectives
Automation Concepts, Selenium configuration, WebDriver Basics | Automation Concepts, Selenium configuration, WebDriver Basics | 1 | WebDriver Basics and Project Deliverables | Self-Paced Learning | Selenium WebDriver MasterClass for Automation Testing | Coverage of the scope in Section 12 and 13 | https://cognizant.udemy.com/course/selenium-webdriver-web-based-automation-testing/ | This course enables associates in Selenium Automation + Java Basics core + Framework design ( TestNG, Pageobject, Excel Datadriven) | In this course, you will learn Selenium WebDriver Basics and Commonly used methods and locator types - Id, Name, Class Name, Link Text, Partial Link Text, Xpath, Css Selector
|  |  |  | Quiz |  | Quiz on Selenium Fundamentals and WebDriver Basics and locators
|  |  |  | HandsOn |  | Hands On on Selenium Webdriver , Driver setup
|  |  |  | Coding Challenge |  | A scenario for which learner has to instantiate the web driver and integrate the locator strategy
Selenium Automation Techniques, Dynamic Xpath | Selenium Automation Techniques, Dynamic Xpath | 1 | Automation Techniques and Dynamic XPath Project Deliverables | Self-Paced Learning | Selenium WebDriver MasterClass for Automation Testing | Coverage of the scope in Section 14 to Section 20 | https://cognizant.udemy.com/course/selenium-webdriver-web-based-automation-testing/ | This course enables associates in Selenium Automation + Java Basics core + Framework design ( TestNG, Pageobject, Excel Datadriven) | In this course, you'll learn the bottle necks faced during selenium automation, How to customize xpath, End to End Automation using all UI Elements with selenium , Handling Java Alerts using Selenium Webdriver. This course also give strong exposure on Synchronization usage in Selenium webdriver
|  |  |  | Quiz |  | Quizes from Selenium Absolute and Relative Xpath, UI Elements recognization challenges , Java Alerts, Siblings and parent- child nodes, Synchronization - Implicit and Explicit wait , Javascript Executor, Ajax, Handling multiple windows
|  |  |  | HandsOn |  | HandsOn on Relative and Absolute xpath, Alerts, Handling multiple windows, Frames, Javascript executor
|  |  |  | Coding Challenge |  | A scenario for which learner has to demonstrate End to End Automation using all UI Elements with selenium webdriver, dynamic Xpath, Java alerts, Javascript Executor, synchronization
Selenium Webdriver With POM and ApachePOI | Selenium Webdriver With POM and ApachePOI | 1 | Page Object Model Framework with Apache POI | Self-Paced Learning | Selenium WebDriver MasterClass for Automation Testing | Coverage of the scope in Section 21 to Section 22 | https://cognizant.udemy.com/course/selenium-webdriver-web-based-automation-testing/ | This course enables associates in Selenium Automation + Java Basics core + Framework design ( TestNG, ANT, Pageobject, Maven, Jenkins, Excel Datadriven, Cucumber, log4j ) + Selenium Grid + DataBase Testing + Performance Testing on Selenium scripts + Mobile testing Basics | In this course you will learn the techniques used for table grid & webtable, Javascript Executor. It enables you to create customized POM Framework with Apache POI
|  |  |  | Quiz |  | Quizes from Hybrid framework, Pageobject model, Apache POI
|  |  |  | HandsOn |  | HandsOn on Selenium Webdriver with POM and Apache POI
|  |  |  | Coding Challenge |  | A scenario for which learner has to demonstrate End to End Automation using page object model and Apache POI. Like Hybrid framework
Automation Testing - Selenium with TestNG | Automation Testing - Selenium with TestNG | 2 | Selenium with TestNG and Junit Selenium with XML/JSON | Self-Paced Learning | 1) Selenium WebDriver MasterClass for Automation Testing 2) JSON and XML for Writers | Coverage of the scope in section 11 from course | https://cognizant.udemy.com/course/selenium-webdriver-web-based-automation-testing/ |  | After completing the the course you will be able to write automated tests using selenium webdriver with TestNg and Junit annotations
|  |  |  | Quiz |  | Learn API Technical Writing: JSON and XML for Writers | https://cognizant.udemy.com/course/api-documentation-1-json-and-xml/learn/lecture/2123580#overview
|  |  |  | Quiz |  | Quizes from TestNG and JUnit basics and annotations
|  |  |  | HandsOn |  | HandsOn on Selenium hybrid framework With TestNG and Junit
|  |  |  | Coding Challenge |  | This is iterative coding challenge. A scenario for which learner has to demonstrate End to End Automation using page object model ,Apache POI, TestNG and JUnit annotations
Digital technologies | Web Services [Concepts, SoapUI & Postman] | 1 | SOAP UI webservices Postman | Self-Paced Learning | 1) WebServices/Rest API Testing with SoapUI +Real time Projects 2) POSTMAN API Testing - Step by Step for Beginners | SoapUI- WebServices/Rest API Testing with SoapUI +Real time Projects Coverage of the scope in Section 1 to Section 8 PostMan - POSTMAN API Testing - Step by Step for Beginners https://cognizant.udemy.com/course/postman-api-testing-step-by-step-for-beginners/ Coverage of the scope in all sections | https://cognizant.udemy.com/course/webservices-testing-with-soap-ui/ https://cognizant.udemy.com/course/postman-api-testing-step-by-step-for-beginners/ |  | After completing the the course you will be able to , Understand Web services, open standards such as TCP/IP, HTTP Illustrate Webservices API Automation Testing using Rest Assured API and POSTMAN Demonstrate API tests using JavaScript with PostMan features Implementing BDD with Cucumber for Selenium Automation. Develop feature file, scenarios, step files, write Cucumber tests and (as part of Cucumber learning) Cucumber Data Tables which handle large amounts of data and the different aspects of Data Tables. Integrate Automation suite with JENKINS to execute scheduled tests. Schedule your automation suite using Devops(Continuous integration). Understand the basics of WhiteBoxTesting Tools
|  |  |  | Quiz |  | Tekstac Quiz for Milestone 5 • Quiz 2 - Webservices Quiz
|  |  |  | HandsOn |  | Tekstac Hands-On • Analyze the WSDL and provide the information requested. Simple SOAP UI web services project with WSDL (Exercise 2) Simple SOAP UI web services project with WADL (Exercise 3) Creation of new PostMan request with collection (Exercise 4)
|  |  |  | Coding Challenge |  | Tekstac SOAP UI and webservices Coding challenge
| BDD and cucumber |  | BDD fundamentals Cucumber | Self-Paced Learning | For BDD fundamentals Cucumber: Selenium WebDriver MasterClass for Automation Testing | This course is designed to Master the BDD concepts with Cucumber Coverage of the scope in Section 26 to Section 29 | https://cognizant.udemy.com/course/selenium-webdriver-web-based-automation-testing/
|  |  |  | HandsOn |  | Tekstac Hands-On : Simple cucumber project with phptravels Simple cucumber project using datatable Simple cucumber project using scenario outline
| Devops | 1 | GIT GRID JENKINS MAVEN | Self-Paced Learning | For Devops:Selenium WebDriver MasterClass for Automation Testing | In this course(Selenium WebDriver MasterClass for Automation Testing), For Maven: Coverage of the scope in Section 10 only For GIT, Jenkins, Selenium Grid: Coverage of the scope in Section 24 and Section 31 only | https://cognizant.udemy.com/course/selenium-webdriver-web-based-automation-testing/
|  |  |  | HandsOn |  | Tekstac Hands-On GIT installation & commands implementationAssignment Setup Grid and parallel executionAssignment Install Jenkins and Creation of new job Mavenization using Eclipse M2E plugin Options and CLI commandsAssignment
|  |  |  | Quiz |  | Quiz 2 : BDD and cucumber Quiz with Devops
Integrated Capability Test (ICT) - SELENIUM (SBA)

## TOC_Functional Testing
Topic # | Topic Name | Topic Objective
1 | Introduciton to Functional Testing | What and Why of Software Testing. Importance of s/w testing with examples of how much impactful it is to business in the digital world, to cost.
2 | Introduction to Test Levels | Provide a view of how testing is being performed at different levels (unit, system, system integration, UAT)
3 | Test Types | Choice of black, white box \with functional and non-functional testing
4 | Test Plan | A walk through of pre-defined plan with emphasis on main sections that provide clarity to the testing project or program
5 | Test Design and development | Overview of test design, types of test scenarios, need of RTM, Test case development techniques - Boundary Value Analysis, Equivalence Partitioning, Decision Table. Walkthrough on sample test cases along with hands on test scenarios and test case writing for BRISK app flow.
6 | Write Test Cases | Write test cases for test scenarios
7 | Test Data | Importance of test data in test design with example of test data and incorporate test data into JIRA / ALM
8 | Expore JIRA | A walk thru of features that is necessary to perform BRISK based hands on.
9 | Test Execution | Execute test cases written in JIRA
10 | Defect Life Cycle | Introduce and walk thru defect stages and life cycle
11 | Defect tracking | Log, track and close the defects for failed TCs
12 | Reviews | Why reviews? Use of checklists. Peer review hands on with the TCs written
13 | Recap | Test Summry report walkthrough, issues encounter and lesson learnt, Defect Causal Analysis Any queries in STLC

## TOC_BU Selenium
Selenium Course - TOC
Chapter | Chapter Name | Topic
Chapter 1 | Selenium Basics and overview | Introduction to Browser Automation
What is Selenium and Overview
History and evolution of Selenium
Selenium Components (WebDriver vs Selenium IDE vs Selenium Grid)
Supported programming languages (Java, Python, C#, etc.)
Cross-browser and cross-platform compatibility.
Advantages and limitations of Selenium
HandsON :TekStac Platform
Chapter 2 | Selenium Architeture | What is Selenium Webdriver: 1) WebDriver is one of the component in selenium. 2) WebDriver is a java interface. 3) WebDriver is an API( Application Programming interface)
Understanding the WebDriver Architecture / API methods. WebDriver, RemoteWebDriver, ChromeDriver , FirefoxDriver, EdgeDriver etc..
Chapter 3 | Setting up Selenium environment | Installing Java Development Kit (JDK) and Eclipse IDE
Downloading Selenium WebDriver
Configuring Selenium WebDriver with Eclipse
HandsON :TekStac Platform
Chapter 4 | Selenium WebDriver | Locating GUI Elements in Application Under Test (AUT)
How to identify the locators in web page
First Selenium Webdriver Script
Launching Browsers in Selenium
HandsON :TekStac Platform
Chapter 5 | Locating various Web elements | Find Element by Id,Name,Link Text,Partial Link Text,Class Name,CSS ( Tag , ID , Class , Attribute , etc..)
Handling Shadow DOM in Selenium
HandsON :TekStac Platform
Relative Locators and Chained Locators in Selenium
Locating By Xpath (Single Slash, Double Slash , contains(), starts_with() , text() , Last())
HandsON :TekStac Platform
Find options in dropdown. Handle dropdown without using Select Class
Find Radio Element
Find Element by Tag Name
Chapter 6 | Desired capabilities | Desired Capabilities in Selenium WebDriver
HandsON :TekStac Platform
Chapter 7 | selenium webDriver commands and Web elements interactions | Selenium WebDriver- Commands
Text fields and buttons
Find Element VS FindElements in Selenium WebDriver - check order
Handling Canvas Elements in Selenium
Using JavaScript Executor in Selenium
HandsON :TekStac Platform
Chapter 8 | WebDriver Actions | Mouse and keyboard actions
Drag and drop
Handling frames and windows
mouse hover (tool tip) in Selenium
Handling tabs & cookies
HandsON :TekStac Platform
Chapter 9 | Multiple windows & frames | Switching between windows
Switching to frames & iFrames
| WebDriver Waits | Implicit waits
Explicit waits
Fluent waits
HandsON :TekStac Platform
Chapter 10 | Selenium Automation Techniques | Checkbox Handling and Form Submission
Locating Web Element Attributes using CSS Selector
Locating Web Element Attributes using Absolute XPath Locator
HandsON :TekStac Platform
Identifying Ancestors of Web Elements
Working with alerts
Working with Java script executor
Working with Regular expression
Working with Drag and Drop and Slider
HandsON :TekStac Platform
Chapter 11 | Advanced WebDriver techniques | Selenium - ScreenShot
Handling JavaScript/window Alerts
Headless browsers and drivers in Selenium
Handling Dynamic Elements in Selenium
HandsON :TekStac Platform
1) get methods , 2) conditional methods, 3) browser methods, 4) navigational methods, 5) wait methods
How to Find All/Broken links using Selenium Webdriver
HandsON :TekStac Platform
Chapter 12 | Calendar using action | Selenium - DatePicker(Actions Class)
| Apache POI | Apache POI - Read Operation : Excel Read Operation
Apache POI - Write Operation: Excel Write Operation
Applying POI POM- Flight reservation
HandsON :TekStac Platform
Chapter 13 | TestNG Concepts | TestNG Assertions
Introduction to TestNG
Creating TestNG test cases
TestNG annotations and assertions
Data-Driven Testing in TestNG
Running Tests in Parallel using TestNG
HandsON :TekStac Platform
Multi-browser testing using TestNG*
Rerun failed tests*
Set Test priority in TestNG
Dependency in TestNG
Soft /Hard Assertion in TestNG
TestNG Report Generation in Selenium WebDriver*
Customize, PDF & Email TestNG Reports in Selenium WebDriver*
HandsON :TekStac Platform
| TestNG Class | TestNG with two test classes
| Data driven | Data driven from XML + POM : Contact Book- POM structure
HandsON :TekStac Platform
Chapter 14 | Test Automation Frameworks | Introduction to Automation Frameworks
Data-Driven Testing in Selenium
Keyword-Driven Testing Framework in Selenium
Page Factory
Building a Modular Testing Framework in Selenium
HandsON :TekStac Platform
Hybrid Framework
| Design Patterns (POM) | Understanding Page Object Model (POM) in Selenium
Creating Page Classes in Selenium
HandsON :TekStac Platform
Implementing Page Factory in Selenium
Design Patterns in Automation using Selenium (Singleton, Factory etc.)
Chapter 15 | Test Data Handling | Reading and Writing Data to Files (e.g., Excel, CSV , XML, JSON) using Java
HandsON :TekStac Platform
Test Data Parameterization in Selenium
Chapter 16 | Test Report and Test Log | Generating Detailed Test Reports (Extent Reports, Allure Reports)
Screenshot Capture Strategies in Selenium
Custom Logging with Log4j in Selenium
HandsON :TekStac Platform
Chapter 17 | Selenium Grid | Introduction to Selenium Grid
Setting up Selenium Grid
Running tests on Selenium Grid
Achieving Parallel Execution in the Cloud
Setting up selenium grid in a docker/K8S container
HandsON :TekStac Platform
| Distributed Execution | Running Tests on Cloud-Based Selenium Grids (e.g., Sauce Labs, Browser Stack)
Achieving Parallel Execution in the Cloud
HandsON :TekStac Platform
| Maven | Introduction to Maven
Creating and Managing Maven Projects
Maven Build Lifecycle (e.g., clean, compile, test, package
| Git Version Control | Introduction to Version Control
Git Fundamentals (Commits, Branches, Merges)
Git Workflow (Pull Requests
Managing Code Repositories on GitHub or GitLab
HandsON :TekStac Platform
| Jenkins CI Systems | Introduction to CI/CD and DevOps
Jenkins Overview and Jobs Configuration
Integrating Selenium Tests into Jenkins Pipelines
Groovy Script Introduction and Syntax
HandsON :TekStac Platform

## TOC_DevOps
Topic # | Topic Name | Topic Objective
1 | Set Up GIT | Install and set up GIT Master and Branches
| GIT Commands | Basic commands of GIT
| Case Study | Use Java Case Study Code: 'Check in, check out, resolve conflicts, merge
2 | Maven - Set Up | Set up as eclipse plugin as well as standalone
| Maven - Basics | Why a build tool and project management/depency tracking tool
| POM.XML | Walk thru of the POM xml
| CLI | Maven command line interfaces
| Case Study | Mavenize the 2 case studies of Java and execute successfully from CLI
3 | Jenkins - Set Up | Install and set up Jenkins
| Configure Jenkins | Configure jobs and integrate with Maven references for auto kick off
| Case Study | Make changes for auto kick off of tests
4 | Grid - Set Up | Install and set up Grid
| Configure Hub/Nodes | Configure and start the hub against 10 machines in classroom as nodes
| Case Study | Execute the test with 100+ iterations

## TOC_HCFacets
Topic Name | Topic Objective
Healthcare Domain | Basic Concepts of Health Insurance and evolution Of Health Plans & Affordable Care Act
Health Plan Benefits and Networks
Provider Compensation Methods
Various Types Health Plans
Consumer Directed Health Plans
Provider Organizations
Utilization Management and Review
Underwriting, Rating and Financing
Claim Administration
Government Programs
Facets Domain | Basic Concepts of Health Insurance and evolution Of Health Plans & Affordable Care Act
Health Plan Benefits and Networks
Various Types Health Plans
Consumer Directed Health Plans
Provider Organizations
Utilization Management and Review
Underwriting, Rating and Financing
Claim Administration
Government Programs

## TOC_GenAI learning
GEN AI LEARNINGS
Topic name | Course name | Delivery mode | Links
Neural Networks | The Complete Neural Networks Bootcamp: Theory, Applications | E-Learning | https://cognizant.udemy.com/course/the-complete-neural-networks-bootcamp-theory-applications/?src=sac&kw=The+Complete+Neural+Networks+Bootcamp%3A+Theory%2C+Applications
GenAI Course | GENERATIVE AI GUIDE: DALL-E, CHATGPT, AND CREATIVITY WITH AI | E-Learning | https://cognizant.udemy.com/course/generative-ai-guide-dall-e-chatgpt-and-creativity-with-ai/
ChatGPT | ChatGPT Masterclass - The Ultimate Guide | E-Learning | https://cognizant.udemy.com/course/chatgpt-complete-masterclass/
Cognizant Gen AI Platform | Cognizant Flowsource 101 foundation program [101-BASICS] (ELRNG02089)GEN AI Learnings | E-Learning | ELRNG02089
Introduction to Responsible AI | Responsible AI-Deep Dive [101- BASICS] | E-Learning | https://COGNIZANTLEARNING.sumtotal.host/core/pillarRedirect?relyingParty=LM&url=app%2Fmanagement%2FLMS_ActDetails.aspx%3FActivityId%3D2216335%26UserMode%3D0

## TOC_Github Copilot - Coverage
Prompt Engineering
Topic | Key Coverage / Outcome
Prompt Engineering | Prompting techniques, best practices, ethics, hands-on lab
GitHub Copilot
Topic | Key Coverage / Outcome
Introduction to GitHub Copilot | Overview of GitHub Copilot features
Setup and Configuration | Beginner-friendly coding with Copilot
Core Features and Capabilities | • Code suggestions and completions • Writing functions and boilerplate code • Generating comments and documentation • Refactoring and optimizing code • Creating test cases
Security and Ethical Considerations | • Understanding AI-generated code risks • Licensing and attribution concerns • Data privacy and usage policies • Responsible use of Copilot
Best Practices | • Reviewing AI-generated code • Combining Copilot with manual coding • Using Copilot for learning new languages • Avoiding over-reliance